## Project Effort Report
Issue # | Summary of tasks | Estimated Effort (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors
1 | Creating comparison layout, lifestyle categories, columns for user/match -traits, habits, matches, and description box for AI compatibility report. | 65 | 65 | 70 | Bryan Kikugawa | Bryan Kikugawa
2 | Linking profiles, and implementing backend data retrieval via user database and AI prompting for compatibility and first message prompts. | 180 | 180 | 155 | Bryan Kikugawa | Bryan Kikugawa
3 | Created a mock user overview card, compatibility, and quick matches. Still need to make the format better. | 90 | 90 | 54 | Anh Minh Nguyen | Anh Minh Nguyen
4 | Adjusting Compatibility Highlights format. | 60 | 60 | 57 | Anh Minh Nguyen | Anh Minh Nguyen
5 | Creating UI for displaying matches in a grid or list with photos and basic info. | 120 | 120 | 16 | Katelynn Crouch | Katelynn Crouch
6 | Connecting match details page to match details button on browse matches page. | 120 | 120 | 6 | Katelynn Crouch | Katelynn Crouch
7 | Creating a mockup admin home page that contains sections and tables for User Management, Content Moderation, and Lifestyle Categories. | 150 | 150 | 129 | Kyla Kanemoto | Kyla Kanemoto
8 | Creating a UserManagement component with a table of users. Adding placeholder search, filter controls, and sortable column headers. | 120 | 120 | 122 | Kyla Kanemoto | Kyla Kanemoto
9 | Creating a ContentModeration component with a table of flagged content. Adding placeholder resolve/deactivate buttons, search, and filter controls. | 120 | 120 | 109 | Kyla Kanemoto | Kyla Kanemoto
10 | Creating a LifestyleCategoryEditor component with list of categories. Adding placeholder add, edit, delete buttons, and search and filter controls. | 90 | 90 | 74 | Kyla Kanemoto | Kyla Kanemoto
11 | Creating the “What is Mānoa RoomieMatch?” landing-page section with responsive layout, styled text, placeholder icons, and cross-device checks. | 300 | 300 | 34 | Adones Morales | Adones Morales
12 | Implementing the “Start Matching” CTA in the hero section with matching styling, anchor behavior, and accessibility tagging. | 180 | 180 | 30 | Adones Morales | Adones Morales
13 | Implementing multi-step form for lifestyle questions, step navigation, question components, and validation + state management. | 90 | 90 | 120 | Kincade Morimoto | Kincade Morimoto
14 | Adding progress bar and autosave behavior using local storage or backend API, and restore-from-draft functionality. | 60 | 60 | 46 | Kincade Morimoto | Kincade Morimoto
15 | Linking Quick Match Access button to the Browse Matches Page/Match Details page + top 3 compatible roommates with key compatibility factors. | 60 | 60 | 30 | Anh Minh Nguyen | Anh Minh Nguyen
16 | Adding ManoaRoomieMatch logo to nav bar. | 10 | 10 | 15 | Katelynn Crouch | Katelynn Crouch
17 | Fixing deployment issue with Vercel. | 60 | 60 | 45 | Katelynn Crouch | Katelynn Crouch
18 | Reformatting landing page. Added components and information included in the mockup. | 120 | 120 | 80 | Everyone | Everyone
19 | Removing "Add Stuff" and "List Stuff" Pages on Nav Bar for normal accounts. Viewable on admin. | 15 | 15 | 9 | Katelynn Crouch | Katelynn Crouch
20 | Creating the top user profile overview (photo, name, quick stats). Used mockup for spacing and widget structure. | 120 | 120 | 38 | Katelynn Crouch | Katelynn Crouch
21 | Checking that all buttons look similar in style with green as accent color. Fixing styling of cards on profile page to match home page. | 45 | 45 | 19 | Katelynn Crouch | Katelynn Crouch
22 | Implemented Edit Profile Page and formatted other pages. | 25 | 25 | 11 | Katelynn Crouch | Katelynn Crouch
23 | Adjusting and linking sign up page. | 120 | 28 | 40 | Anh Minh Nguyen | Anh Minh Nguyen
23a | Connecting user profile to the database and read/edit live info. | 60 | 114 | 20 | Anh Minh Nguyen | Anh Minh Nguyen
24 | Implement accept match, save for later, pass buttons and link them to necessary routes + refine admin logic. | 120 | 164 | 34 | Kyla Kanemoto | Kyla Kanemoto
25 | Implementing compatibility scoring. | 120 | 14 | 12 | Katelynn Crouch | Katelynn Crouch
26 | Creating endpoint for match list. | 180 | 170 | 25 | Bryan Kikugawa | Bryan Kikugawa
27 | Removing mock data and connecting real API. | 300 | 54 | 87 | Adones Morales | Adones Morales
28 | Providing data for match detail view. | 200 | 23 | 58 | Adones Morales | Adones Morales
30 | Implementing a messaging system mockup and adding a message icon for user. | 120 | 127 | 17 | Kyla Kanemoto | Kyla Kanemoto
31 | Implementing admin API and removing hard coded elements from admin page. Adding admin-only endpoints. | 180 | 155 | 14 | Kyla Kanemoto | Kyla Kanemoto
32 | Updating sign-in page to match rest of site theme. | 60 | 45 | 5 | Kincade Morimoto | Kincade Morimoto
32a | Fixing an error that doesn’t let you create new user profiles. | 60 | 40 | 3 | Kincade Morimoto | Kincade Morimoto
33 | Updating the front end of comparison page. | 150 | 120 | 20 | Bryan Kikugawa | Bryan Kikugawa
34 | Updating and improving UI of user profile and connect edit profile to database. | 120 | 48 | 10 | Anh Minh Nguyen | Anh Minh Nguyen
35 | Making lifestyle survey results save to database so users can match. | 45 | 30 | 10 | Bryan Kikugawa | Bryan Kikugawa
36 | Making footer green and adding bold “Manoa Roomie Match” above template footer. | 10 | 4 | 0 | Katelynn Crouch | Katelynn Crouch
37 | Adjusting and adding to schema and update database. | 120 | 32 | 63 | Anh Minh Nguyen | Anh Minh Nguyen
38 | Implementing function to view other user's profile. | 60 | 23 | 8 | Kyla Kanemoto | Kyla Kanemoto
39 | Updating the admin page by adding a functioning sidebar, removing unnecessary pages, and ensuring correct admin tables and routes. | 250 | 231 | 30 | Kyla Kanemoto | Kyla Kanemoto
40 | Adding a delete button for users to delete their profiles and records in the database. | 30 | 28 | 84 | Anh Minh Nguyen | Anh Minh Nguyen
41 | Making sure user can update their profile picture in edit profile page and display it in their profile page. | 120 | 127 | 46 | Anh Minh Nguyen | Anh Minh Nguyen
42 | Implementing functionality of admin buttons (category add button, action buttons in user management). | 90 | 156 | 18 | Kyla Kanemoto | Kyla Kanemoto
43 | Fixing admin delete button in user management. | 60 | 32 | 0 | Kyla Kanemoto | Kyla Kanemoto
44 | Updating the About Me section to include Lifestyle Survey info while keeping Edit Profile minimal. | 120 | 96 | 14 | Katelynn Crouch | Katelynn Crouch
44a | Update My Profile and Edit Profile pages to fetch real matches and redirect back after saving. | 90 | 19 | 40 | Anh Minh Nguyen | Anh Minh Nguyen
45 | Creating a page with helpful resources for finding a place to live. | 60 | 26 | 11 | Katelynn Crouch | Katelynn Crouch
46 | Adding graphics across the application. | 30 | 47 | 13 | Katelynn Crouch | Katelynn Crouch
47 | Implementing that only @hawaii.edu emails are allowed to create an account, and adding help for finding @hawaii.edu address. | 90 | 60 | 0 | Kincade Morimoto | Kincade Morimoto
48 | Implementing Playwright tests to verify all pages load correctly and all forms function properly with valid inputs. | 30 | 23 | 16 | Everyone | Everyone
49 | Implementing the message dropdown buttons. | 90 | 36 | 10 | Kyla Kanemoto | Kyla Kanemoto
50 | Creating a separate database for storing messages between users. | 120 | 100 | 30 | Bryan Kikugawa | Bryan Kikugawa
51 | Replacing hardcoded messaging with dynamic user-specific messaging. | 90 | 60 | 15 | Bryan Kikugawa | Bryan Kikugawa
52 | Adding a report user button to user profiles, and routing report button to content moderation table on admin side and connect to database. | 120 | 182 | 48 | Kyla Kanemoto | Kyla Kanemoto
53 | Fixing sign up page and its redirection. | 60 | 46 | 12 | Anh Minh Nguyen | Anh Minh Nguyen
54 | Adjusting the navbar layout to be proportional and dynamic on any device. | 300 | 28 | 15 | Adones Morales | Adones Morales
55 | Testing all clickable elements and confirming they route to the correct pages or modals. | 200 | 21 | 18 | Adones Morales | Adones Morales
56 | Implementing automatic prompt to new user to add profile information after lifestyle survey. | 30 | 23 | 0 | Katelynn Crouch | Katelynn Crouch
57 | Fixing the admin management buttons' connection to database | 90 | 60 | 12 | Kyla Kanemoto | Kyla Kanemoto
58 | Adding filter and sort tool to browse matches. | 60 | 19 | 0 | Katelynn Crouch | Katelynn Crouch
59 | Removing outdated/false information about user. | 50 | 27 | 0 | Katelynn Crouch | Katelynn Crouch
60 | Deleting the hard-coded /home page and redirecting the user to their profile page. | 60 | 42 | 18 | Anh Minh Nguyen | Anh Minh Nguyen
61 | Fixing the report from user side, cleaning up buttons, adding notifications, and allowing admin to assign admin role. | 200 | 153 | 36 | Kyla Kanemoto | Kyla Kanemoto
62 | Routing lifestyle categories to manage user side and creating a campus life page. | 60 | 71 | 14 | Kyla Kanemoto | Kyla Kanemoto
63 | Reviewing all pages for hard coded stuff + check style and themes | 120 | 180 | 0 | Kincade Morimoto | Kincade Morimoto
63a | Deleted "Potential Conflicts" and "AI Compatibility Report" boxes because they are hard coded | 10 | 10 | 2 | Anh Minh Nguyen | Anh Minh Nguyen
64 | Checking playwright tests. | 60 | 74 | 33 | Kyla Kanemoto | Kyla Kanemoto

## Total Development Experience
Team Member | Software Development Experience (months) | How was coding effort tracked? | How was non-coding effort tracked?
Kyla Kanemoto | 4 | WakaTime | Toggl
Kincade Morimoto | 4 | Phone/Desktop Clock | Phone/Desktop Clock
Bryan Kikugawa | 4 | Watch/Desktop clock | Watch/Best Guess
Adones Morales |  | Watch | Watch
Katelynn Crouch |  | Phone/Desktop Clock | Phone/Desktop Clock
Anh Minh Nguyen | 4 | Phone timer | Phone timer

## Kyla
Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors | Milestone | Tracking method
7 | Created a mockup admin home page that contains sections and tables for User Management, Content Moderation, and Lifestyle Categories. | 150 | 150 | 129 | Kyla Kanemoto | Kyla Kanemoto | 1
8 | Created a UserManagement component with a table of users. Added placeholder search, filter controls, and sortable column headers. | 120 | 120 | 122 | Kyla Kanemoto | Kyla Kanemoto | 1
9 | Created a ContentModeration component with a table of flagged content. Added placeholder resolve/deactivate buttons, search, and filter controls. | 120 | 120 | 109 | Kyla Kanemoto | Kyla Kanemoto | 1
10 | Created a LifestyleCategoryEditor component with list of categories. Added placeholder add, edit, delete buttons, and search and filter controls. | 90 | 90 | 74 | Kyla Kanemoto | Kyla Kanemoto | 1
30 | Implemented a messaging system mockup and added message icon for user. | 120 | 127 | 17 | Kyla Kanemoto | Kyla Kanemoto | 2
31 | Implemented admin API and removed hard coded elements from admin page. Added admin-only endpoints. | 180 | 155 | 14 | Kyla Kanemoto | Kyla Kanemoto | 2
42 | Implemented functionality of admin buttons (category add button, action buttons in user management). | 90 | 156 | 18 | Kyla Kanemoto | Kyla Kanemoto | 2
43 | Fixed admin delete button in user management. | 60 | 32 | 0 | Kyla Kanemoto | Kyla Kanemoto | 2

## Kincade
Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors | Milestone | Tracking method
13 | Implement multi-step form for lifestyle questions (sleep schedule, noise tolerance, cleanliness, etc.). Step navigation Question components Validation + state management | 90 | 120 | 5
14 | Do all work for this task in a branch called issue-14. Add progress bar and autosave behavior using local storage or backend API. Progress bar component Autosave hook Restore-from-draft functionality | 60 | 46 | 5

## Bryan
Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors | Milestone | Tracking method
1 | "Implement Match Details Page Mockup" - Comparison layout - Lifestyle categories - Display columns for user/match -traits, habits, matches - Description box for AI compatibility report | 65 | 70 | 25 | Bryan Kikugawa | Bryan Kikugawa | 1
2 | "Implement Basic Components on Match Details Backend" - Linking profiles - Backend data retrieval via user database - AI prompting for compatibility and first message prompts | 180 | 155 | 10 | Bryan Kikugawa | Bryan Kikugawa | 1
26 | "Browse Matches API" - Created endpoint for match comparison page - Created API components for match comparison page - Added local test-data scripts | 180 | 170 | 25 | Bryan Kikugawa | Bryan Kikugawa | 2
33 | "Update Comparison page Layout" - Updated front end of comparison page - Updated comparison page color scheme - Added placeholder functionality for some components on the page | 150 | 120 | 20 | Bryan Kikugawa | Bryan Kikugawa | 2
35 | "Fix matching algorithm" - Created and fixed routes so that lifestyle survey completion would save to database | 45 | 30 | 10 | Bryan Kikugawa | Bryan Kikugawa | 3
50 | "Create messaging database" - Created seperate database fields for messaging function - Updated prisma schema - Added API routes for messaging functionality | 120 | 100 | 30 | Bryan Kikugawa | Bryan Kikugawa | 3
51 (51a are error fixes to Issue 51; combined time for both are recorded in "Issue 51") | "Updated Messaging functionality/Fixed Messaging Errors" - Replaced mockup with actual user messages - Created separate pages for individual chats - Created separate page for search function - Added creation of new messages - Added/Updated messaging API routes - Fixed fetch errors for messaging | 90 | 155 | 25 | Bryan Kikugawa | Bryan Kikugawa | 2,3

## Adones
Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors | Milestone | Tracking method
11 | Implement Platform Explanation Section | 300 | 35 | 40 | Adones Morales | Adones Morales | 1 | Watch
12 | Add “Start Matching” Call-to-Action Button | 180 | 30 | 35 | Adones Morales | Adones Morales | 1 | Watch
27 | Integrate Browse Matches UI | 300 | 54 | 87 | Adones Morales | Adones Morales | 2 | Watch
28 | Match Details API | 200 | 23 | 58 | Adones Morales | Adones Morales | 2 | Watch
54 | Improve Layout of Nav Bar | 300 | 28 | 15 | Adones Morales | Adones Morales | 3 | Watch
55 | Verify All Buttons/Links Function | 200 | 21 | 18 | Adones Morales | Adones Morales | 3 | Watch

## Katelynn
Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors | Milestone | Tracking method
5 | Create UI for displaying matches in a grid or list with photos and basic info. | 120 | 16 | 5
6 | Connect match details page to match details button on browse matches page. | 120 | 6 | 4
16 | Add Logo to nav bar | 10 | 15 | 5
17 | Fix deployment issue with Vercel | 60 | 45 | 34
19 | Remove "Add Stuff" and "List Stuff" Pages on Nav Bar for normal accounts. Viewable on admin. | 15 | 9 | 3
20 | Create the top user profile overview (photo, name, quick stats). Use mockup for spacing and widget structure. | 120 | 38 | 5
21 | Make sure all buttons look similar in style. Green as accent color. Fix styling of cards on profile page to match home page. | 45 | 19 | 4
22 | Implement Edit Profile Page and format other pages | 25 | 11 | 5

## Anh Minh
Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Milestone | Tracking method
3 | Created a mock user overview card, compatibility, and quick matches. Still need to make the format better | 90 | 54 | 17 | 1 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
4 | Adjust Compatibility Highlights format | 60 | 57 | 15 | 1 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
15 | Quick Match Access button linking to the Browse Matches Page/Match Details page Including top 3 compatible roommates, key compatibility factors (e.g., sleep schedule, cleanliness, lifestyle preferences) | 60 | 30 | 15 | 1 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
37 | Adjust and add to scheman and update database | 120 | 32 | 63 | 2 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
23 | Adjust and link sign up page | 120 | 28 | 40 | 2 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
23a | Connecting user profile to the database and read/edit live info | 60 | 114 | 20 | 2 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
34 | Update and improve ui of user profile and connect edit profile to db | 120 | 48 | 10 | 2 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
53 | Fixed sign up page and its redirection | 60 | 46 | 12 | 3 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
44a | Improved the My Profile page and Edit Profile page by fetching real matched user's from Browse Matches page and redirect user back to their profile page after saving changes | 90 | 19 | 40 | 3 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
40 | Add delete button for user to delete their profile and record in the database | 130 | 28 | 84 | 3 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
41 | Implement profile picture for user | 120 | 127 | 46 | 3 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
60 | Delete the hard-coded /home page and reroute user to their profile page. When new user sign up, they are added to the database, but stuck at sign up page with error message | 60 | 42 | 18 | 3 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period
63a | Deleted "Potential Conflicts" and "AI Compatibility Report" boxes because they are hard coded | 10 | 10 | 2 | 3 | Record start and end time on phone's timer, write down each timestamp for coding and non-coding period